Video & Voice Calling Feature

Status Report

Prepared for: Engineering Manager   |   Date: 29 August 2026

Scope: Self-hosted WebRTC video/voice calling for iLive (FastAPI + MongoDB backend, React Native mobile app, browser test client), built against the "Command Centre-Initiated Video Consultation with Patient" epic spec.

# 1. Summary

Of the 32 requirement areas in the epic, 19 are complete and verified against a real backend, 8 are partially complete, and 5 have not been started -- all 5 of those require a real mobile device and native build tooling (push notifications, native call UI) that isn’t available in the current build environment. Every completed item is backed by automated tests: 295 checks across 14 test suites, all passing, plus a clean TypeScript check on the mobile app. Testing this thoroughly also caught and fixed 3 real bugs before they would have reached users -- details in Section 5.

Bottom line: everything that can be built and tested without a physical phone is done or in progress. What remains is native mobile integration (needs a device), a handful of small polish items, and a short list of decisions that need your (or Business/Medical) sign-off -- see Section 6.

# 2. Completed

Fully implemented and verified against the real backend.

| Item | What it covers | Status | Notes |
| --- | --- | --- | --- |
| Access control & multi-tenant scoping | Configurable roles/permissions; users, appointments, and calls are scoped to a tenant and can’t cross tenant boundaries. | Done | Also closed a real cross-tenant data leak found while testing this (see Section 5). |
| Call flow & call states | Full invite → ringing → accept/decline → connect → end → history flow, with the epic’s exact state names and end-reason codes. | Done |  |
| Ringing timeout, decline, cancel | Unanswered calls auto-expire (45s default); clean handling when the patient declines or the caller cancels. | Done |  |
| One call at a time | A user already on a call can’t be double-booked into another one; caller/patient get a clear "busy" state. | Done |  |
| Multiple patient devices | Rings every device the patient is logged into; first one to answer wins, others are told "answered elsewhere." | Done |  |
| Camera/mic permission handling & audio-only fallback | Automatic fallback to audio-only on poor video is off by default and requires an explicit setting to enable; every occurrence is logged distinctly from a manual switch. | Done | Was previously always-on; closed a compliance risk against the epic’s requirements. |
| Network quality & adaptive video | Live good/fair/poor network indicator shown to both sides; outbound video quality automatically steps down/up to match the peer’s connection. | Done |  |
| Reconnect as the same device | A browser refresh or an app crash-and-restart reconnects into the same in-progress call rather than losing it. | Done | Verified this reporting period against the real backend. |
| Call recording | Intentionally not built, matching the epic’s "disabled for V1" requirement. | Done |  |
| Call history & audit trail | Every call logs initiator, timestamps, end reason, platform, interruption/reconnection counts. | Done |  |
| Post-call notes & outcome | Doctor can record notes and an outcome (resolved / follow-up / referred / escalated) after a call ends, on web and mobile. | Done |  |
| Missed-call messaging | Friendly "you missed a call from X" notice instead of the call screen just disappearing. | Done |  |
| Logging, monitoring & alerting | Every call event is logged and queryable; genuine backend failures raise alerts and can push to a Slack-style webhook. | Done |  |
| Analytics events | 13 distinct event types (call started/connected/declined/dropped/etc.) queryable per call. | Done |  |

# 3. In Progress / Partially Done

Some of the requirement is built; the rest is either minor polish or waiting on native mobile work.

| Item | What it covers | Status | Notes |
| --- | --- | --- | --- |
| Pre-call device checks | Camera/mic and browser-compatibility checks before a call starts. | In progress | Done. Still missing: app-version and push-notification-token checks, both of which need the native mobile work below. |
| Calling-experience polish | Ringing timer, network indicator, camera/mic device picker (web). | In progress | Device picker shipped this period. Still missing: minimize/picture-in-picture view. |
| Patient incoming-call screen | Caller name, media type, consent checkbox; optional "iLive Care Team" display name instead of the doctor’s real name. | In progress | Identity-masking option is built and off by default. Still missing: iLive visual branding, and the native OS incoming-call screen (needs native work). |
| Camera/audio controls | Mute, camera on/off, front/rear camera switch, speaker routing. | In progress | All done except Bluetooth headset/speaker selection. |
| Call-session security token | A short-lived, signed token scoped to a specific call and user. | In progress | Token is built and issued. Not yet wired in as an access-control check anywhere -- today’s checks against the database already cover this; needs a concrete use case before it’s worth adding. |
| Error-message wording | Matching the exact wording the epic specifies for each error case. | In progress | Error codes all exist; wording is still this build’s own draft copy. Blocked on getting the epic’s literal approved text to match against. |
| Backend readiness for native calling | Server-side pieces a future push-notification system will need. | In progress | Call-locking and analytics are done. Still missing: actually sending push notifications and managing device tokens (native work). |

# 4. Not Started

All five items below need the same thing: a real mobile phone and native build tooling (Xcode/Android Studio, physical device testing) that this environment doesn’t have. None of them can be meaningfully started without that.

| Item | What it covers | Status | Notes |
| --- | --- | --- | --- |
| Receiving calls in the background | Getting a call while the app is backgrounded, closed, or the phone is locked -- needs push notifications plus native call UI (iOS CallKit / Android Telecom). | Not started | Everything else in this report assumes the app is open in the foreground. |
| Cellular call interruption | What happens if a regular phone call comes in during a video consult. | Not started | Depends on the item above. |
| Detecting an existing cellular/VoIP call | Preventing a video call from starting while the patient is already on a phone call. | Not started | Depends on native integration. |
| BLE device coexistence | Making sure a video call doesn’t interfere with any Bluetooth vitals-monitoring devices (smartband, ECG, BPM) the patient may be using. | Not started | No existing BLE monitoring code in this app to integrate with yet -- needs a scoping discussion on where that lives. |
| Real-device / cross-platform QA | Running the app on actual Android and iOS phones and tablets. | Not started | Automated testing (295 checks) covers everything that can be tested without physical hardware. |

# 5. Testing & Quality

295 automated checks across 14 test suites (backend + client-side logic), all passing, plus a fully clean TypeScript check on the mobile app. Every feature above marked Done was verified against a real running backend before being called complete, not just reviewed by eye.

Building out this testing surfaced and fixed three real bugs that would otherwise have shipped:

- A crash in the call-invite handler that could take down signaling for other users, not just the call being placed.

- A cross-tenant data leak where the user list endpoint could return users from a different tenant/organization.

- A camera/microphone failure (permission denied, device busy, etc.) left one side of a call frozen and the other side ringing forever, instead of failing cleanly for both.

# 6. Decisions Needed From You / Business / Medical

These are pending sign-off, not engineering work. Several have a working default already in place so the team isn’t blocked, but none are formally confirmed:

- Which roles can initiate a Command Centre call (currently just a placeholder "doctor" role).

- Whether patients see the clinician’s real name or a generic "iLive Care Team" label (built, off by default).

- Ringing timeout (defaulted to 45s) and reconnection grace period (defaulted to 30s).

- Whether automatic audio-only fallback should be allowed at all, and under what conditions (built, off by default).

- Minimum supported Android/iOS versions and approved browsers.

- Call-log retention period.

- Patient consent wording (current draft has not been reviewed by Legal/Medical).

- Post-call outcome categories (current list is an engineering draft, not Medical-reviewed).

# 7. Recommended Next Steps

- Decide whether to invest in native mobile development (device + Xcode/Android Studio access) to unlock Section 4 -- this is the single biggest remaining chunk of work.

- Share the epic’s literal error-message copy so wording can be reconciled (Section 3, error-message item).

- Review and confirm the open decisions in Section 6 so defaults can be finalized or changed before a real deployment.